## Sheet1
S.no | Title | Component | Responsible | Status | Bench details | Start Date | Delivery Date | Remarks/Comments
1 | ACVW_ADAS_2023_2479 | CVM | Venkata Seshaiah | Started | RT3 | 2023-11-28 | 2023-11-30 | In Progress
2 | ACVW_ADAS_2023_2482 | PSA Lib | Vignesh K | Yet To Start | NA | 2023-11-30 | 2023-12-06 | Checking Inputs For the Activity
3 | ACVW_ADAS_2023_2478 | FRDR | Sindhuja Reddy | Started | NA | 2023-11-29 | 2023-12-01 | In Progress
4 | ACVW_ADAS_2023_2480 | PSA Lib | Shaik Mastan | Yet To Start | NA | 2023-11-30 | 2023-12-01 | Checking Inputs For the Activity
5 | ACVW_ADAS_2023_2466 | PSA Lib | Azeem Basha | Started | NA | 2023-11-16 | 2023-12-05 | In Progress
6 | ACVW_ADAS_2023_2435 | FRDR | Bharath B | Started | NA | 2023-11-27 | 2023-12-06 | In Progress
7 | ACVW_ADAS_2023_2472 | FRDR | Masilaadevi R | Started | NA | 2023-11-27 | 2023-12-01 | In Progress
8 | ACVW_ADAS_2023_2475 | PSA Lib | Nagababu Viswanathapalli | Yet To Start | NA | 2023-11-30 | 2023-12-08 | Checking Inputs For the Activity
9 | ACVW_ADAS_2023_2474 | FRDR | Ganesh Shetty | Started | RT8 | 2023-11-23 | TBD | In Progress
10 | ACVW_ADAS_2023_2481 | PSA Lib | Kalpana Sinha | Yet To Start | NA | 2023-11-30 | 2023-12-01 | Checking Inputs For the Activity